## PO_Header
Purchase Order Revision Header
Field | Value
PO ID | PO-7194
Addendum | 02
Effective deadline | 2026-07-02
Revision reason | site layout update
Currency | USD
Revised schedule total | 6276

## Base_Schedule
Protected Base Purchase Order Schedule
Line ID | Description | Quantity | Unit price | Unit | Extended total | Protected
PO-01 | Valve kits | 20 | 120 | each | 2400 | No
PO-03 | Cable trays | 56 | 56 | USD per unit | 3136 | No
PO-04 | Site safety signage | 4 | 16 | each | 64 | Yes

## Revised_Schedule
Revised Purchase Order Schedule
Line ID | Description | Quantity | Unit price | Unit | Extended total | Revision status
PO-01 | Valve kits | 22 | 120 | each | 2640 | quantity changed
PO-02 | Commissioning | 1 | 140 | visit | 140 | inserted
PO-03 | Cable trays | 56 | 61 | USD per unit | 3416 | unit price changed
PO-04 | Site safety signage | 5 | 16 | each | 80 | unchanged
| Revised schedule total |  |  |  | 6276

## Revision_Log
Addendum Revision Log
Line ID | Change type | Old value | New value | Source page
PO-01 | quantity changed | 20 each | 22 each | 1
PO-02 | inserted | Not in base schedule | $140.00 / visit | 1
PO-03 | unit price changed | $56.00 / unit | $61.00 / unit | 1

## Provenance
Addendum Source Traceability
Line ID | Source document | Page | Text locator | Target row
PO-01 | po_addendum.pdf | 1 | po_addendum.pdf:p1:valve-kits | Revised_Schedule!4
PO-02 | po_addendum.pdf | 1 | po_addendum.pdf:p1:commissioning | Revised_Schedule!5
PO-03 | po_addendum.pdf | 1 | po_addendum.pdf:p1:cable-trays | Revised_Schedule!6

## Checks
PO Revision Integrity Checks
Check | Observed | Expected | Interpretation
Changed/inserted rows | 3 | 3 | All addendum changes applied
Protected base line | CHECK | PASS | PO-04 remains unchanged
Revised schedule total | 6276 | 6260 | Formula-linked total