## PO_Header
Purchase Order Revision Header
Field | Value
PO ID | PO-8820
Addendum | 03
Effective deadline | 2026-07-29
Revision reason | mechanical routing revision
Currency | USD
Revised schedule total | 7430

## Base_Schedule
Protected Base Purchase Order Schedule
Line ID | Description | Quantity | Unit price | Unit | Extended total | Protected
PO-11 | Pump skids | 12 | 310 | each | 3720 | No
PO-13 | Conduit bundles | 40 | 48 | USD per unit | 1920 | No
PO-14 | Safety barriers | 6 | 75 | each | 450 | Yes

## Revised_Schedule
Revised Purchase Order Schedule
Line ID | Description | Quantity | Unit price | Unit | Extended total | Revision status
PO-11 | Pump skids | 14 | 310 | each | 4340 | quantity changed
PO-12 | Factory acceptance test | 1 | 520 | visit | 520 | inserted
PO-13 | Conduit bundles | 40 | 53 | USD per unit | 2120 | unit price changed
PO-14 | Safety barriers | 6 | 75 | each | 450 | unchanged
| Revised schedule total |  |  |  | 7430

## Revision_Log
Addendum Revision Log
Line ID | Change type | Old value | New value | Source page
PO-11 | quantity changed | 12 each | 14 each | 1
PO-12 | inserted | Not in base schedule | $520.00 / visit | 2
PO-13 | unit price changed | $48.00 / unit | $53.00 / unit | 1

## Provenance
Addendum Source Traceability
Line ID | Source document | Page | Text locator | Target row
PO-11 | confirm_po_addendum.pdf | 1 | confirm_po_addendum.pdf:p1:pump-skids | Revised_Schedule!4
PO-12 | confirm_po_addendum.pdf | 2 | confirm_po_addendum.pdf:p2:factory-test | Revised_Schedule!5
PO-13 | confirm_po_addendum.pdf | 1 | confirm_po_addendum.pdf:p1:conduit-bundles | Revised_Schedule!6

## Checks
PO Revision Integrity Checks
Check | Observed | Expected | Interpretation
Changed/inserted rows | 3 | 3 | All addendum changes applied
Protected base line | PASS | PASS | PO-04 remains unchanged
Revised schedule total | 7430 | 7430 | Formula-linked total